## 1_Project Team List
Project Team List
| Forename 姓名 | Title 职务 | Phone No. 座机 | Mobile 移动电话 | Company Mail 邮箱 | Project Meeting Attendee Record
2023
[6 empty] | 2023-08-14 | 2023-08-21 | 2023-08-28 | 2023-09-04 | 2023-09-11 | 2023-09-18 | 2023-09-25 | 2023-10-02 | 2023-10-09 | 2023-10-16 | 2023-10-23 | 2023-10-30 | 2023-11-06 | 2023-11-13 | 2023-11-20 | 2023-11-27 | 2023-12-04 | 2023-12-11 | 2023-12-18 | 2023-12-25
A - Daimler
1 | Wang Nan(Rock) | Supplier Management (AT) | N.A. | 18145687651 | bfda.ww.wang@daimlertruck.com
2 | Cheng Haifeng | Procurement |  | 13601065759 | haifeng.cheng@daimlertruck.com
3 | Queiroz, Ricardo Campelo | RD lead |  | 15600597336 | ricardo.c.queiroz@daimlertruck.com
4 | Liu,junping | RD |  | 13581857672 | mbbu.l.liu@daimlertruck.com
5 | Yu,Tong | LFT Lead |  | 13321183933 | mbbu.lm.yu@daimlertruck.com
4
5
B - Goldrare
1 | Yongjiang Feng | CEO |  | 18531226186 | fengyongjiang@bjghrc.com
2 | Xiaofeng Zhang | CTO |  | 18610772508 | zhangxiaofeng@bjghrc.com
3 | Changhai Pan | Overseas Business Minister |  | 18673399353 | panchanghai@bjghrc.com
4 | Dongfang Wang | Overseas Business Engineer |  | 18511780380 | wangdongfang@bjghrc.com
5 | Zhang Xiao | Project Director |  | 13520373887 | zhangxiao@bjghrc.com
6 | Xi Lv | Project Manager |  | 15652535136 | lvxi@bjghrc.com
7 | Yongfei Xia | Advanced Quality Minister |  | 18612905826 | xiayongfei@bjghrc.com
8 | Lin Tao | AQE |  | 15003321624 | lintao@bjghrc.com
9 | Xilong Wang | SQE |  | 13716448256 | wangxilong@bjghrc.com
10 | Dong Su | Test |  | 18612905893 | sudong@bjghrc.com
11 | Liu Haiying | Purchasing Engineer |  | 18510181922 | liuhaiying@bjghrc.com
12 | Jingqian Feng | Processing Minister |  | 18610139692 | fengjingqian@bjghrc.com
13 | Liu Menghao | Processing Engineer |  | 15512898386 | liuronghao@bjghrc.com
14 | Li Ning | Designing Engineer |  | 19213058797 | lining@bjghrc.com
17 | Wei Chen | Plant Quality Minister |  | 18611025833 | chenwei@bjghrc.com
18 | Yanyu Ge | Plant Technical Vice President |  | 18611025833 | geyanyu@bjghrc.com
19 | Lei Wang | Plant Manager |  | 17301166323 | wanglei@bjghrc.com
20 | Wei Wang | Production Minister |  | 19831788717 | wangwei@bjghrc.com
21 | Hongbo Liang | Styling Manager |  | 18612905849 | lianghongbo@bjghrc.com
22 | Fa Wang | E-coating Manager |  | 19831788700 | wangfa@bjghrc.com
23 | Jianheng Ni | Foaming Mangaer |  | 1365410737 | nijianheng@bjghrc.com
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
Key Team Member
Team member as Supporter or Supervisor
Key Team Member
Team member as Supporter or Supervisor

## 2_Timing Plan (hidden)
H6 Lower Extendable Bunk 进度计划 H6 Lower Extendable Bunk Timing Plan
Part Name | H6 Lower Extendable Bunk | Status | Overdue
VGU No. |  |  | Finished
Part No. | A9619709549 |  | In process
Supplier Name | Beijing Goldrare Automobile Parts Co., Ltd |  | Not start
Timing Plan | Steps | Status |  | Start Date DD.MM.YYYY | Complete Date DD.MM.YYYY | Resp. | 20 23 | 20 23 | 20 23 | 20 23 | 20 23 | 20 23 | 20 23 | 20 23 | 20 23 | 20 23 | 20 23 | 20 23 | 20 23 | 20 23 | 20 23 | 20 23 | 20 23 | 20 23 | 20 23 | 20 23 | 20 23 | 20 23 | 20 23 | 20 23 | 20 23 | 20 23 | 20 23 | 20 23 | 20 23 | 20 23 | 20 23 | 20 23 | 20 23 | 20 23 | 20 23 | 20 23 | 20 23 | 20 23 | 20 23 | 20 23 | 20 23 | 20 23 | 20 23 | 20 23 | 20 23 | 20 23 | 20 23 | 20 23 | 20 23 | 20 23 | 20 23 | 20 23 | 20 23 | 20 23 | 20 23 | 20 23 | 20 23 | 20 23 | 20 23 | 20 23 | 20 23 | 20 23 | 20 23
[7 empty] | Jan. |  |  |  |  | Feb. |  |  |  |  | Mar. |  |  |  |  | Apr. | [5 empty] | May. |  |  |  |  | Jun. |  |  |  |  | Jul. | [5 empty] | Aug. |  |  |  |  | Sep. |  |  |  |  | Oct. |  |  |  |  | Nov. |  |  |  |  | Dec.
[7 empty] | 01 | 02 | 03 | 04 | 05A | 05B | 06 | 07 | 08 | 9A | 9B | 10 | 11 | 12 | 13A | 13B | 14 | 15 | 16 | 17 | 18A | 18B | 19 | 20 | 21 | 22A | 22B | 23 | 24 | 25 | 26A | 26B | 27 | 28 | 29 | 30 | 31A | 31B | 32 | 33 | 34 | 35A | 35B | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44A | 44B | 45 | 46 | 47 | 48A | 48B | 49 | 50 | 51 | 52 | 53A
Timing Plan |  | Not start | Plan |  |  |  | Apr. 13B: 13B; Nov. 44B: 44B
|  |  | Actual |  |  |  | Apr. 13B: 13B; Nov. 44B: 44B
|  | Not start | Plan |  |  |  | Apr. 13B: 13B; Nov. 44B: 44B
|  |  | Actual |  |  |  | Apr. 13B: 13B; Nov. 44B: 44B
|  | Not start | Plan |  |  |  | Apr. 13B: 13B; Nov. 44B: 44B
|  |  | Actual |  |  |  | Apr. 13B: 13B; Nov. 44B: 44B
|  | Not start | Plan |  |  |  | Apr. 13B: 13B; Nov. 44B: 44B
|  |  | Actual |  |  |  | Apr. 13B: 13B; Nov. 44B: 44B
|  | Not start | Plan |  |  |  | Apr. 13B: 13B; Nov. 44B: 44B
|  |  | Actual |  |  |  | Apr. 13B: 13B; Nov. 44B: 44B
|  | Not start | Plan |  |  |  | Apr. 13B: 13B; Nov. 44B: 44B
|  |  | Actual |  |  |  | Apr. 13B: 13B; Nov. 44B: 44B
| P Release | Finished | Plan | N.A. | 17.01.2023 | R&D Daimler | bar: Jan. 03
|  |  | Actual | N.A. | 17.01.2023 | bar: Jan. 03
| Issue P Released Drawings to Goldrare | Finished | Plan | N.A. | 17.01.2023 | R&D Daimler | bar: Jan. 03
|  |  | Actual | N.A. | 17.01.2023 | bar: Jan. 03
| P Released Drawings Confirmation | Finished | Plan | 18.01.2023 | 03.02.2023 10.02.2023 | Goldrare | bar: Jan. 03 to Feb. 05B
|  |  | Actual | 18.01.2023 | 10.20.2023 | bar: Jan. 03 to Feb. 06
| Issue SA to Goldrare | Finished | Plan | 18.01.2023 | 31.01.2023 | Procurement BFDA | bar: Jan. 03 to Jan. 05A
|  |  | Actual | 18.01.2023 | 30.01.2023 | bar: Jan. 03 to Jan. 05A
| SA Confirmation | Finished | Plan | 01.02.2023 | 03.02.2023 | Goldrare | bar: Feb. 05B
|  |  | Actual | 31.01.2023 | 06.02.2023 | bar: Feb. 05B to Feb. 06
| Tooling Preparation | Finished | Plan | 06.02.2023 | N.A. | Goldrare | bar: Feb. 06 to Apr. 14
|  |  | Actual | 07.03.2023 | N.A. | bar: Feb. 06 to Apr. 14
| Tooling Ready | Finished | Plan | 07.03.2023 | 07.04.2023 | Goldrare | bar: Feb. 06 to Apr. 14
|  |  | Actual | 07.03.2023 | 07.04.2023 | bar: Feb. 06 to Apr. 14
| Gauge Preparation | Finished | Plan | 06.02.2023 | N.A. | Goldrare | bar: Feb. 06 to Apr. 14
|  |  | Actual | 07.03.2023 | N.A. | bar: Feb. 06 to Mar. 13A
| Gauge Ready | Finished | Plan | N.A. | 07.04.2023 | Goldrare | bar: Feb. 06 to Apr. 14
|  |  | Actual | N.A. | 927.03.2023 | bar: Feb. 06 to Mar. 13A
| Raw Material and Sub-Components Preparation | Finished | Plan | 06.02.2023 | 31.03.2023 | Goldrare | bar: Feb. 06 to Mar. 13A
|  |  | Actual | 01.03.2023 | 31.03.2023 | bar: Feb. 06 to Mar. 13A
| Raw Material and Sub-Components Ready | Finished | Plan | 01.04.2023 | 07.04.2023 | Goldrare | bar: Feb. 06 to Apr. 13B
|  |  | Actual | 01.04.2023 | 07.04.2023 | bar: Feb. 06 to Apr. 13B
| Production Line Preparation (Include Production Trial Run) | Finished | Plan | 10.04.2023 22.05.2023 | 28.04.2023 08.06.2023 | Goldrare | bar: May. 21 to Jun. 23
|  |  | Actual | 22.05.2023 | bar: May. 21 to Jun. 23
| Production Line Ready | Finished | Plan | 04.05.2023 09.06.2023 | 04.05.2023 12.06.2023 | Goldrare | bar: Jun. 23 to Jun. 24
|  |  | Actual | 09.06.2023 | 12.06.2023 | bar: Jun. 23 to Jun. 24
| Production of Samples | Not start | Plan | 04.05.2023 | 05.05.2023 | Goldrare
Actual
| Inspection of Samples | Not start | Plan | 04.05.2023 | 05.05.2023 | Goldrare
Actual
| Delivery of Samples | Not start | Plan | 08.05.2023 | 10.05.2023 | Goldrare
Actual
| DVP (Design Verification Plan) | Finished | Plan | 18.01.2023 | 03.02.2023 08.02.2023 17.02.2023 | Goldrare | bar: Jan. 03 to Feb. 08
|  |  | Actual | 18.01.2023 | 10.02.2023 | bar: Jan. 03 to Feb. 08
| DV Test | Finished | Plan | 08.05.2023 | 15.05.2023 17.06.2023 | Goldrare | bar: May. 19 to Jun. 24
|  |  | Actual | 04.03.2023 | bar: Mar. 9B to Jun. 25
| DVP&R (Design Verification Plan and Report) | In process | Plan | 16.05.2023 | 19.05.2023 23.06.2023 03.07.2023 07.07.2023 | Goldrare | bar: May. 20 to Jul. 27
|  |  | Actual | 04.03.2023 | 07.07.2023 | bar: Mar. 10 to Aug. 32
| To issue Tooling Modification Order to Goldrare | Finished | Plan | 04.07.2023 | 31.07.2023 | Procurement BFDA | bar: Jul. 27
|  |  | Actual | 04.07.2023 | 06.07.2023 | bar: Jul. 27
| Short Term Solution Parts Preparation (Aug. and Sep.) | Finished | Plan | 01.07.2023 | 15.07.2023 | Goldrare | bar: Jul. 26B to Jul. 28
|  |  | Actual | 01.07.2023 | 15.07.2023 | bar: Jul. 26B to Jul. 28
| Tooling Modification ( Please see plan) | In process | Plan | 17.07.2023 | 30.08.2023 | Goldrare | bar: Jul. 29 to Aug. 35A
|  |  | Actual | 17.07.2023 | bar: Jul. 29 to Aug. 32
| 1st batch production and process audit | Not start | Plan | 04.09.2023 | 08.09.2023 | Goldrare | bar: Sep. 36
Actual
| PPAP Documents Submission | Not start | Plan | N.A. | 15.09.2023 | Goldrare | bar: Sep. 37
Actual
| Blank Release | Not start | Plan | N.A. | 15.09.2023 | R&D BFDA | bar: Sep. 37
Actual
| PPAP Approval | Not start | Plan | 18.09.2023 | 28.09.2023 | SM BFDA | bar: Sep. 38 to Sep. 39
Actual
| Delivery from Goldrare to BFDA | Not start | Plan | 11.09.2023 | 22.09.2023 | Logistics BFDA | bar: Sep. 37 to Sep. 38
Actual
| SOP at BFDA | Not start | Plan | 01.03.2025 | 01.07.2025 | All | bar: Oct. 41
Actual
| Blank Release | Not start | Plan | N.A. | 30.04.2023 | R&D Daimler
Actual
| Issue Blank Released Drawings to Goldrare | Not start | Plan | 01.05.2023 | 05.05.2023 | Procurement BFDA
Actual
| Raw Material and Sub-Components Preparation | Not start | Plan
Actual
| Raw Material and Sub-Components Ready | Not start | Plan
Actual
| Process Audit | Not start | Plan | 15.05.2023 | 19.05.2023 | SM BFDA
Actual
| PPAP Documents Preparation | Not start | Plan | N.A. | 26.05.2023 | Goldrare
Actual
| PPAP Documents Submission | Not start | Plan | N.A. | 26.05.2023 | Goldrare
Actual
| PPAP Documents Check | Not start | Plan | 29.05.2023 | 02.06.2023 | SM BFDA
Actual
| PPAP Approval | Not start | Plan | 05.06.2023 | 09.06.2023 | SM BFDA
Actual
| P.O. of First Batch SOP Parts | Not start | Plan | N.A. | 09.06.2023 | Logistics BFDA
Actual
| Raw Material and Sub-Components Preparation | Not start | Plan
Actual
| Raw Material and Sub-Components Ready | Not start | Plan
Actual
| Production of First Batch SOP Parts | Not start | Plan | 12.06.2023 | 23.06.2023 | Goldrare
Actual
| Pick Up of First Batch SOP Parts | Not start | Plan | 26.06.2023 | 28.06.2023 | Logistics BFDA
Actual
| SOP at BFDA | Not start | Plan | 01.07.2023 | 01.07.2023 | BFDA
Actual
|  | Not start | Plan
Actual
|  | Not start | Plan
Actual
Today

## 2_ Timing Plan
H6 Extendable Lower Bunk Project development timing plan | [7 empty] | Beijing Foton Daimler Mercedes-Benz BU
Part Group | H6 Cabin Extended |  |  |  | Status | Overdue | Maturity Level
Part Name | H6 Extended Lower Bunk |  |  |  |  | Finished
Part No. | A9619709549 |  |  |  |  | In process
Supplier Name | Beijing Goldrare Automobile Parts Co., Ltd |  |  |  |  | Not start
Project Steps |  | Status |  | Duration （Days) | Start Date DD.MM.YYYY | Complete Date DD.MM.YYYY | Year | 2022 |  | 2023 | [11 empty] | 2024 | [11 empty] | 2025
[7 empty] | Quarter | Q4 |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4
[7 empty] | Month | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
ML
SA / Contract 签订合同 |  | Finished | Plan | 10 | 2022-12-12 | 2022-12-22
Actual
Project Kick off 项目启动 |  | Finished | Plan | 1 | 2022-12-16 | 2022-12-17
Actual
Supply chain development 供应链开发 |  | In process | Plan | 300 | 2023-01-01 | 2023-10-28
Actual
Sub-components design fix for tier II,n supplier tier II, n...供应商零部件设计放行 |  | Finished | Plan | 51 | 2022-11-01 | 2022-12-22
Actual
Supply chain nomination for tier II, tier n… tier II, n...供应链定点 |  | Finished | Plan | 61 | 2022-11-01 | 2023-01-01
Actual
Samples production & inspection @ sub-supplier 分供方样件生产和检验 |  | Finished | Plan | 30 | 2023-08-05 | 2023-09-04
Actual
Samples delivery from sub-supplier 分供方提交样件 |  | Finished | Plan | 7 | 2023-09-04 | 2023-09-11
Actual
Sub-components PPAP @ sub-supplier 分供方零件PPAP放行 |  | Not start | Plan | 60 | 2024-07-30 | 2024-09-28
Actual
Sub-components SOP @ sub-supplier 分供方零件量产交付 |  | Not start | Plan | 30 | 2024-09-30 | 2024-10-30
Actual
B pro Sample development B pro 样件开发 |  | Finished | Plan | 160 | 2023-01-17 | 2023-06-26
Actual
Design release for B pro sample manufacture kick-off 用于启动B样件制作的设计放行 |  | Finished | Plan | 30 | 2022-12-19 | 2023-01-18
Actual
B pro sample production 样件生产制造 |  | Finished | Plan | 120 | 2023-02-16 | 2023-06-16
Actual
Part Delivery 零件送达 |  | Finished | Plan | 118 | 2023-02-28 | 2023-06-26
Actual
Seires Tooling development 量产工装开发 |  | In process | Plan | 280 | 2023-06-27 | 2024-04-02
Actual
Design release for tooling kick-off 用于启动工装的设计放行 |  | Finished | Plan | 180 | 2023-06-27 | 2023-12-24
Actual
Tooling manufacturing 工装制作 |  | In process | Plan | 80 | 2023-12-24 | 2024-03-13
Actual
C sample production C 样件生产 |  | In process | Plan | 50 | 2023-03-13 | 2023-05-02
Actual
Production facility & gauge development 生产设备和检具开发 |  | Not start | Plan | 160 | 2024-03-05 | 2024-08-12
Actual
Production facility & gauge design 生产设备和检具设计 |  | Not start | Plan | 30 | 2024-03-05 | 2024-04-04
Actual
Production facility & gauge manufacturing 生产设备和检具制作 |  | Not start | Plan | 70 | 2024-04-04 | 2024-06-13
Actual
Pre-acceptance at producer site 制造现场预验收 |  | Not start | Plan | 10 | 2024-06-14 | 2024-06-24
Actual
Transfer to supplier Plant 转移到供应商工厂 |  | Not start | Plan | 10 | 2024-06-24 | 2024-07-04
Actual
Production facility & gauge installation and set up 生产设备和检具安装调试 |  | Not start | Plan | 40 | 2024-07-04 | 2024-08-13
Actual
DVP test 样件测试 |  | Not start | Plan | 213 | 2023-09-30 | 2024-04-30
Actual
DVP sample production DVP测试样件生产 |  | Not start | Plan | 150 | 2023-09-11 | 2024-02-08
Actual
DVP test @ supplier DVP测试@供应商 |  | Not start | Plan | 15 | 2024-02-08 | 2024-02-23
Actual
Sample delivery for bench test @ BFDA MBBU 台架测试样件交付@ BFDA MBBU |  | Not start | Plan | 10 | 2024-02-08 | 2024-02-18
Actual
Sample bench test @ BFDA MBBU & supplier 在BFDA MBBU和供应商端的样件台架测试 |  | Not start | Plan | 20 | 2024-02-08 | 2024-02-28
Actual
Sample delivery for vehicle test 整车测试样件交付 |  | Not start | Plan | 15 | 2024-02-08 | 2024-02-23
Actual
Vehicle Level test 整车级别测试 |  | Not start | Plan | 129 | 2023-10-24 | 2024-03-01
Actual
Blank release 设计“_"放行 |  | Not start | Plan | 30 | 2024-04-01 | 2024-05-01
Actual
Packaging & logistics development 包装和物流开发 |  | Not start | Plan | 87 | 2024-03-01 | 2024-05-27
Actual
logistics concept alignment 物流方案确定 |  | Not start | Plan | 7 | 2024-03-21 | 2024-03-28
Actual
packaging proposal alignment 包装方案确定 |  | Not start | Plan | 20 | 2024-03-01 | 2024-03-21
Actual
Packaging delivery try-run 包装方案交付试验 |  | Not start | Plan | 30 | 2024-03-21 | 2024-04-20
Actual
Try-run result evaluation & optimization 试验结果评估和改进 |  | Not start | Plan | 30 | 2024-04-20 | 2024-05-20
Actual
Packaging proposal approval 包装方案批准 |  | Not start | Plan | 7 | 2024-05-20 | 2024-05-27
Actual
Process & Product Approval 过程和产品放行 |  | Not start | Plan | 90 | 2024-09-30 | 2024-12-29
Actual
PPAP documents preparation PPAP 文件 准备 |  | Not start | Plan | 90 | 2024-09-30 | 2024-12-29
Actual
PPAP production line setting up PPAP 生产线调试 |  | Not start | Plan | 40 | 2024-09-30 | 2024-11-09
Actual
Trial-run production for PPAP production & audit PPAP生产和审核前的试生产 |  | Not start | Plan | 20 | 2024-11-09 | 2024-11-29
Actual
Production line setting up after PPAP trial run PPAP试生产后的产线调整 |  | Not start | Plan | 10 | 2024-11-30 | 2024-12-10
Actual
PPAP production & audit PPAP生产&审核 |  | Not start | Plan | 5 | 2024-11-30 | 2024-12-05
Actual
PPAP Sample delivery PPAP 样件交付 |  | Not start | Plan | 5 | 2024-12-05 | 2024-12-10
Actual
PPAP Sample inspection @ BFDA MBBU PPAP 样件在 BFDA MBBU的检验 |  | Not start | Plan | 25 | 2024-11-30 | 2024-12-25
Actual
PPAP批准 Supplier PPAP approvel |  | Not start | Plan | 15 | 2024-12-16 | 2024-12-31
Actual
SOP @ BFDA MBBU 量产 @ BFDA MBBU |  | Not start | Plan | 120 | 2025-01-01 | 2025-05-01
Actual
SOP at Supplier Plant 供应商工厂SOP |  | Not start | Plan | 15 | 2025-01-01 | 2025-01-16
Actual
First shipment production after SOP SOP后首批次零件生产 |  | Not start | Plan | 5 | 2025-01-16 | 2025-01-21
Actual
First shipment inspection & testing 首批次零件检测 |  | Not start | Plan | 5 | 2025-01-21 | 2025-01-26
Actual
First shipment delivery to BFDA MBBU 首批次零件发运至 BFDA MBBU |  | Not start | Plan | 2 | 2025-01-26 | 2025-01-28
Actual
SOP @ BFDA MBBU BFDA MBBU 工厂SOP |  | Not start | Plan | 30 | 2025-03-01 | 2025-03-31
Actual
3 months monitoring for project close 追踪3个月项目关闭 |  | Not start | Plan | 90 | 2025-03-31 | 2025-06-29
Actual
Formulas:
Overdue = [Status]+E10
Overdue = E112+[Status]

## 3_Open Issue List
Project Open Issues List
| Update Date | 07.11.2023 |  |  | Part Number | Part Name | Change Level | VGU | Closed
| Project | CXT lower bunk |  |  | A9619709549 | ZB BUNK LWR CABIN2500 | 001 | CXT343001_LB | Finished to be reported
| Supplier | Goldrare | [6 empty] | Processing
| Manufacturing Location | Cangzhou | [6 empty] | Overdue
| Meeting Date | 07.11.2023
| Next Meeting Date | 13.11.2023
Meeting Time:
Call in No. : Participate in China: 4008-096-263 (participants passcode: 49239010) Participate in Turkey: 811 2131 444 (participants passcode: 49239010)
|  |  | Action | Quanty
|  |  | Total | 12
|  |  | Overdue | 0
|  |  | Processing | 10
|  |  | Completed to report | 0
|  | 8 | Closed | 2
|  |  | Close Ratio | 16.67%
No. | Information / Issues | Actions / Comments | Resp. | Planed Duedate DD.MM.YYYY | Completion Status | Actual complete date DD.MM.YYYY | Remark
1 | Scenario for saftey net fix to the Alu frame in order to pass the 29 crash test | 2023/8/14 The latest safety net scenario that benchmark with SFTP will be realized in C2 samples. Info | Rudy Li Ning | 30.08.2023 | Closed | 14.08.2023
2 | Brackets enhance data for the CAE simulation | 2023/8/14 Latest Brackets new data sent by Goldrare last Thursday and BTV will have some improvements then send to CAE simulation and result will be shared in weeks 2023/08/21: Send the latest data include safety net modified and also solve the collision issue with refrigerator by this Wednesday. 2023/08/28: Goldrare needs to audit the data again and sent out the final version. 2023/09/04：Missing Screws for suppprt plastic parts 2023/09/11:Left side C channle needs to be moved towards inside 0.7mm. A collsion between Cap and screw needs to be considered. 2023/09/18：C channel already moved, shorter lock screw is used, the collision is avoided. 2023/09/25：Needs Asif's feedback. 2023/10/09：Confirmened by BFDA. | Rudy Asif | 30.08.2023 | Closed
3 | collision betweet bunk handle and refrigerator | 2023/08/14 Asif check there is collision while refrigerator is open. Goldrare reply that they check no collision based on the data they received.Need Goldare and Asif come to alignment. PS:C2 samples will not realize this status and will keep the same with B sample. 2023/08/28: 5 mm space btw handle and storage box left, is this enough? 2023/09/04：Asif will check all components and sent out minimal gap 2023/09/11: 5 mm space is not enough, 10 mm is the minimal requirement. 2023/09/18:10mm space is created. 2023/09/25：Needs Asif's feedback. 2023/10/09：Confirmened by BFDA. | Rudy Asif | 18.08.23 | Closed
4 | scenario between bigger mattress fix to Alu frame | 2023/08/07 Daimler accept the connection part scenario between bigger mattress and Alu frame. Info | Rudy Daimler | 07.08.23 | Closed
5 | 29G crash test | 29G in China 2024/01/22：new tooling is redesigned and will be finished on Feb 7th. Two kind of test samples will be prepared: one is with plastic release handle part, the other is fabric pull strip. Both solution will be changed to use M4*25 bolts to fix the cross bar. One of two location holes will be moved to enhence the beam strength. The other two new storage boxes need to be avaliable before Feb 26th. Test pass criteria need to be clarifed. 2024/02/26: a special meeting for test pass criteria will be organized M6 for corssbar is used. We are trying or crossbar to contact Lab to do the test on Friday. 2024/03/11: The latest data needs to be updated to Asif. New 29G crash test will be done on next wednesday. 2024/4/3：The 29G crash test result confirmation is needed for 15 samples preparation and homolation samples. 2024/04/09: Homologation samples can be prepared without confirmation of 29G crash tests? 2024/04/15：A internal discussion within BFDA will be orgainzed for confirmation of 29G crash test. Next week will output a feedback. 2024/04/22: Test result is accepted by Pitler Filix, bolts change needs to be implenmented. A special Email for timeline and chang cost need to be sent out. We need a official confirmation for tooling change. 2024/05/13：Next crash test will be done at end of Mai, 9 samples will be prepared after crash test. 2024/05/20: The crash test will be done on 28th of Mai, at that time Lab will be available. 2024/06/03: The crash test has been done on 28th of Mai. 9 samples are waitting for confirmation. 2024/06/17：9 samples are ready for shipment. | Tim zhang Rudy Peter Ricardo Felix | 30.12.2023 | Processing
Processing
6 | C2 samples | 2024/01/15：The delivery time of New Samples need 50 days(40days for parts purchasing,5 days for assembly, 5 days for delivery). For new order pls. arrange it as early as possible. 2024/01/22: Four new samples can be deliveried after chinese spring festival, because some supplier have holiday very early. The delivery time can be marked in quotation. 2024/02/19: 4 samples in old status, will be deliveried before 29G crash test, the ohter 3 will be deliveried in new status after 29 G Crash test. 2024/03/18:7 samples for homologation in improved status. The 3 samples in new status. Samples delivery depends on the crash test. 2024/04/03: Confim whether homologation samples can be prepared separately without 29g Crash test requirment. The delivery time is about 4 weeks. The delivery time is expected on the 9th or 10th of May. 2024/04/15: Homologation samples will be delivered on 10th of May, the material purcahsing and tooling change need at least 2 weeks. 2024/04/22: Homologation 7 samples +3 prototype samples will be deliveried based on Ricardo's 26th March Eimal confimed status. 2024/05/06: 7 homologation samples + 3 prototype samples will be prepared in next week. 2024/05/20：3 homologation samples with bolts and 1 prototype samples without bolts will be sent out at 21th of Mai, the rest 4 homologation samples with bolts and 2 prototype samples without bolts will be togather with 9 crash test samples without bolt will be prepared at the end of Mai(31th). 2024/06/03:3 samples are already sent to BFDA, 4 samples are ready for shipment. High attention must be given on apprence quality. 2024/06/17: the rest 4 homologation samples were alredy sent out to BFDA. 1 summer test sample is needed（latest status + Locker release handle）. | Tim zhang Rudy Rock wang | th | Processing
7 | DVP TEST | 2024/01/22: Updating DVP plan and project timline accordingly. Sharing test report of last Locking&Extension Durability Test. 2024/02/05: After CNY prepare other mechnical tests parallelly. 2024/03/12:The folding durability test will be on next Friday. 2024/04/03: We have built up the test tooling, and already done 1000 cycles. 2024/04/09: Do the test with new mattresses after confirmation. 2024/04/15: for CQC CERTIFACTION, we need to do DVP first. Waiiting for german confirmation of fabric. It will be double checked, whether CQC will be needed in Spetember or October. 2024/04/22:at the end of august, CQC needs to be finished. 2024/06/17: update DVP list, organize mechnical test first. 2024/06/18: GR imtermally check and update timing plan, which DVP test can be done based on the current status, which one need to be postponed. | Tim zhang Rudy | 09.11.2023 | Processing
8 | Safety net hook position not right | 2023/09/18: The safety net position needs to be adjusted so that the hook can have a right position. 2023/09/25：Needs Asif's feedback. 2023/10/09：Confirmened by BFDA. |  |  | Closed
9 | Connection fabric strip btw. Inner Frame and outer frame needs to be optimized | 2023/09/18: Connection fabric strip btw. Inner Frame and outer frame needs to be optimized.Validate the Maufacutre feasibility and check the data with all the surrounding parts Daimler given. 2023/09/25：Needs Asif's feedback. 2023/10/09: Needs to be checked togather C2 samples status. 2023/10/23: C2 samples report (include parts status and moulding tooling status ) is needed. 2023/11/07: C2 reports need to be sent out. |  |  | Closed
10 | CAE analysis and 29G test 3D data | 2023/10/9: The technical information of U hook need to to collected. The U pillar is 6mm DN, the welding hole is 7mm DN, the plate is 3mm thick. The size of 2 welding foots is 3mm. 2023/10/16: The CAE analysis result will be finishedd in this week. The welding method is arc welding. 2023/10/23: A sepreate meeting for 2nd CAE analysis result. 2023/10/30: The modification caused by CAE will be checked in 29g crash test. 2023/11/20: 1>seat safety of seat impact in CAE. 2>latest data for BUNK. // No update 2023/11/27: latest data have been shared through SWAN. |  |  | Closed
11 | Styling and Fabric | 2023/11/13: Final decision about fabric color and material. Peter and Ricardo will feedback a time in this week. 2024/01/22: keep use Goldrare concept. 2024/06/03: R radius of BUNK need to be output by BFDA. 2024/06/18: Confirm data and styling with Petra on 19th June. After confirmation, prototype can be prepared. |  |  | Processing
12 | Magnet | 2023/11/20: a modified cover with foam with 3 pieces magnets needs to be provide for onsite check. 2023/11/27: a modified sample is provided. 2023/12/11:5 container for different position of magenet in next samples, waitting for height infos. 2024/01/29: 5 container at highst position of backrest. 2024/04/03：Quotation for magnet. 2024/04/15: A simulation will be done today, feedback this afternoon. 2024/04/22: Prepare a new mattress with new position. 2024/05/20: A prototype sample should be assembled with magnet bar. 2024/06/17: A sample is already sent to BFDA, waitting for counterpart to check. |  |  | Processing
13
14
13 | Bolts | 2024/1/29：prepare a addiation ppt for bolts solustion. 2024/02/05:adding bolts torque infos into the slider. |  |  | Closed
14 | Foam | 2024/1/29：Foam still not easy to open, 2 samples with 20mm cut are prepared 2024/02/05: after CNY, GR prepare several foam samples for onsite check which is better. 2024/03/11: a sample with 20mm thicker foam and backrest combined with small mattress need to be prepared. 2024/03/18: Togather with solutions for new requirments based on winter test feedback. |  |  | Closed
15 | Gloss Request | A9609701040 gloss request? 2024/02/26: 2.4±0.2 for the gloss for A9609701040 is confirmed. |  |  | Closed
15 | T-box | 2024/03/18: Hanger is waitting for BTV feedback. Tbox take refrence of SFTP Part. 2024/04/03: purchase right material for part production. 2024/04/08: 9051 is black, it black right color? 2024/04/15: take color code of SFTP, waitting for feedback of Cem. 2022/04/22: Color code is 8N84. Color material searching and size optimation need to be done first. Timling plan needs to be prepared. 2024/05/13: which supplier delivery plastic material of PA6GF30 with 8N84? 2024/05/27:28TH output the tooling modification timeline, based on the current data. 2024/06/17: GR produce some parts in current molding status, 15th July GR should provide new parts with good function and apprence. 2024/06/18: 19th, two hand optimized parts need to be sent to Rock. |  |  | Processing
16 | New requirments | GR need to provede solutions for new requirments this week: 1.Cancel the 3rd foam and combine it with backrest. 2.Improve sewing quality. 3.Rails cut out must be decked. 4.All mattresses have to be straight and have same gap to the wall. 5.The sewing line at the front edge needs to be eliminated. 6.Visible nuts need to be eliminited. 7.Strap need to be optimized to avoide hanger blocking and easy operation. 8. The wood sleds can be feeled, the mattress thickness need to be increased. 2024/04/08：New fixtures will be manufactured，the fixtures for corner part connection need to be confirmed ASAP. 2024/04/15: Next week have a feedback. Fixture will be manufactured as current planed, the bolt 180° turnover, the change with this concept has a cost of 50 000 CNY. 2024/4/22: Front bolt cancelling will be strarted first after Ricardo confirmed, other improvments are waitting for official input. EPP Part price need to be double checked. 2024/05/13: 9 german crash test samples will be in lastest status(cancelling front bolts). |  |  | Processing
17 | Locker release handle | 2024/04/08: tooling kick off.7homolagtion with pull strip, a separate part with plastic handle for evaluation. 2024/04/22: May 10th a simple will be sent to to BFDA to check. 2024/5/13: A samples is installed on V77 truck. Waitting for tooling kickoff. 2024/05/20: Waitting for tooling Supplier feedback. 2024/06/03: Handle part's color, styling and graining need to be output by BFDA. Handle part data should be sent to BFDA first. 2024/06/17: 1. EPP supoort block need a complete prototype for evaluation. 2. Rail cover take 3D printed part for evaluation.3. Locker release handle tooling kickoff follow up. 4. make EPP inner frame sample for evaluation. |  |  | Processing
18 | HydroPuls | a ourter frame needed for hydropulse test, GR needs to check when can delivery a ourter frame part. 2024/5/27: the frame was already exchanged with a new one on 21th. |  |  | Closed
Processing
20 |  | 2024/04/27: New samples delivery should be attached with sample status and measure report. Prepare a summary of all changes to be implemented with a due date.

## 4_DVP Test
H6 SEAT C2-SAMPLE GOLDRARE DV TEST PLAN_V2_20200708
PROJECT项目 |  | TEST TARGET试验对象 |  |  | C2 TEST COMPLETION STATUS SECTION DIAGRAM (After-C2 TESTS NOT INCLUDED) C2试验完成状态示意图(不包括C2之后的试验) |  |  |  |  | C2 TEST STATUS LIST | QUANTITY |  |  | C2 TEST STATUS试验状态
H6 BUNK |  | H6 Extendable Bunk - SOP 2024 | [7 empty] | Pass | 0 |  |  | Pass通过
[10 empty] | Processing | 0 |  |  | Processing进行中
UPDATE更新日期 |  | EDITOR编辑人 | CONTACT联系方式 | [6 empty] | Fail | 0 |  |  | Fail失败
22.06.2022 |  | TIM ZHANG | zhangxiao@bjghrc.com | [6 empty] | Not Start | 0 |  |  | Not Start未启动
[10 empty] | C2 Test Amount | 0 |  |  | C2 Test Delay Conclution试验延迟结论:
SUPPLIER供应商 |  | BEIJING GOLDRARE AUTOMOBILE PARTS CO., LTD | [7 empty] | C2 TEST Passing Rate | #DIV/0!
Performance Objective 性能目标 | No.序号 | Test Name试验名称 | Test Procedure / Method试验过程/方法 | Test Purpose Classification 测试目的分类 | Web_100 Classification Web_100分级 | Testing Report Phase 测试报告阶段 | Standard Source 标准出处 | Acceptance Criteria / Test Target 接受标准/试验目标 | Test Party 试验方 | Start 起始日期 | Complete 完成日期 | Status 状态 | Delay 延迟 | Remark 备注
| 18 | Plastic Part Anti-Environment 塑件环保试验 | 1. Adopt ISO 105-B06 exposure method 2, condition group 3, in 3 cycles. The surface of the sample shall be free of exudates, black spots, chalking, cracks, or obvious change in gloss. Conduct visual inspection according to GB/T 250. Compared with the reserved samples, the color fastness grade shall not be less than 3 to 4. 采用ISO 105-B06曝光方法2，条件组3，共3个循环。样品表面应无渗出物、黑点、白垩斑、裂纹或光泽明显变化。按GB/T 250进行目视检查。与预留样品相比，色牢度等级不得低于3 ~ 4级。 2. Conform to QC/T15-1992. At room temperature, immerse the sample in a container filled by solvents for 2 hours. After drying, the sample shall be free of defects such as cracking, swelling, whitening and discoloration. (all related chemical mediums shall be used) 符合QC/T15-1992。在室温下，将样品浸泡在充满溶剂的容器中2小时。干燥后的样品应无开裂、肿胀、变白、变色等缺陷。(所有相关化学介质应使用) | Chemical 化学 | C | C2 | ISO 105-B06 QC/T 15-1992 | Color Fastness grade shall ＞ = 3-4 After drying, the sample shall be free of defects such as cracking, swelling, whitening and discoloration 色牢度等级为> = 3-4 干燥后的样品应无开裂、肿胀、变白、变色等缺陷 | EMTEK SGS | 2024-08-01 | 2024-08-30 | Not Start 未启动 | No Delay 未延迟 | Waitting for locker release handle
| 19 | Plastic Part Anti-Friction 塑件防摩擦试验 | Conform to GB/T3920. Test frequency: 1 reciprocating friction cycle per second, 10 friction cycles in total. It shall meet the requirements of Article 11 in Table 2 of Q/FT A161-2009. 符合GB/T3920。试验频率：往复摩擦循环每秒1次，共摩擦循环10次。应符合Q/FT A161-2009表2第11条的要求。 | General 常规 | C | C2 | DBL 5306 | To fulfill the requirements of Article 11 in Table 2 of Q/FT A161-2009. 满足Q/FT A161-2009表2中第11条的要求。 | EMTEK SGS | 2024-08-01 | 2024-08-30 | Not Start 未启动 | No Delay 未延迟 | Waitting for locker release handle